## Timeline
ARES — Project Timeline (Gantt)
VI-VII Semester ¦ 2022 Scheme ¦ 32-week roadmap
Task | Owner | W1 | W2 | W3 | W4 | W5 | W6 | W7 | W8 | W9 | W10 | W11 | W12 | W13 | W14 | W15 | W16 | W17 | W18 | W19 | W20 | W21 | W22 | W23 | W24 | W25 | W26 | W27 | W28 | W29 | W30 | W31 | W32
Phase 1: Foundations & Data Pipeline | Sem VI
Register ACLED academic access; set up GDELT/BigQuery | Shirin
Build async ingestion scripts (fetch_acled, fetch_gdelt, fetch_news) | Shirin
Design & migrate PostgreSQL/PostGIS schema (Region_Key model) | Shirin
Literature survey & problem scoping | All
Feasibility study & SRS drafting | All
Phase 2: Feature Engineering & Core Model | Sem VI
Implement rolling feature calculations (accel., volatility, ratio) | Sreshta
Fine-tune DistilBERT sentiment model on news headlines | Sreshta
Build baseline Random Forest risk classifier | Sreshta
Historical backtest design (case selection, data windowing) | Sreshta
Phase 3: Dashboard Prototype (Review 1) | Sem VI
Build mock dashboard with sample data | Tanya
Review 1 preparation & submission | All
Phase 4: Integration & Validation | Sem VII
Integrate live data → features → model → dashboard | All
Run and document historical backtest results | Sreshta
Build interactive heatmap & drill-down views | Tanya
Explainability panel + source-evidence linking | Tanya
Review 2 preparation & submission | All
Phase 5: Hardening & Final Delivery | Sem VII
Testing (unit, integration, model validation) | All
Ethical/bias review pass & documentation | All
Dockerize, .env secrets, CI/CD (optional) | Shirin
Final report, demo video, Review 3 / viva prep | All