## Module Distribution
ARES — Module Distribution Sheet
Ownership across the 3-member team
Module | Path/Location | Description | Owner | Status
Data Ingestion | /ingestion | Async API fetch scripts (ACLED, GDELT, NewsAPI, WorldBank/IMF) | Shirin | In Progress
Database & Schema | /storage | PostgreSQL/PostGIS schema, Region_Key linking, migrations | Shirin | In Progress
Military & Diplomatic Data Stream | /ingestion (data) | Originally Thrisha's stream; retained data, ownership redistributed | Shirin | Not Started
Feature Engineering | /features | Rolling indicators: event acceleration, sentiment volatility, protest ratio | Sreshta | In Progress
NLP Sentiment Model | /model (nlp) | DistilBERT/RoBERTa fine-tuning on news headlines | Sreshta | Not Started
Risk Classification Model | /model (ml) | Random Forest / gradient-boosted risk classifier | Sreshta | Not Started
Historical Backtesting | /model (validation) | Historical case validation & lead-time reporting | Sreshta | Not Started
Backend API | /api | Endpoints serving risk results and region queries to frontend | Tanya | Not Started
Dashboard — Overview | /frontend | Traffic-light cards, interactive heatmap | Tanya | In Progress
Dashboard — Drilldown & Explainability | /frontend | Region drilldown, trend chart, source-evidence panel | Tanya | Not Started
Docker / Deployment | infra | Containerization, .env secrets, optional CI/CD | Shirin | Not Started
Documentation & Reviews | docs | SRS, architecture doc, review decks, final report | All | Ongoing
Owner Summary
Shirin — Data Engineering & Integration Lead: ingestion, database, deployment
Sreshta — AI/ML Model Developer: features, NLP, risk model, backtesting
Tanya — System Development & Visualization Lead: backend API, dashboard, UX