## Risk Register
ARES — Risk Register
Technical, Data, and Project-Management Risks
ID | Risk Description | Category | Likelihood (1-5) | Impact (1-5) | Score (L×I) | Mitigation | Owner
R-01 | API rate limits / quota exhaustion (GDELT BigQuery, NewsAPI) | Technical | 3 | 3 | 9 | Cache raw responses; query only stale windows; batch daily | Shirin
R-02 | Sparse/noisy open-source data for low-coverage regions | Data | 3 | 3 | 9 | Scope MVP validation to high-coverage regions; document limits | Shirin
R-03 | NLP sentiment model bias (Western-trained corpora) | Ethical/Model | 4 | 3 | 12 | Treat as one weighted signal only; disclose limitation; human-in-loop | Sreshta
R-04 | Team member attrition affecting delivery | Project Mgmt | 2 | 4 | 8 | Cross-document ownership; shared data assets; redistribute workload | All
R-05 | Model fails backtest recall/precision targets | Model | 3 | 4 | 12 | Layered model approach: simple baseline first, escalate complexity only if it helps | Sreshta
R-06 | PostgreSQL/PostGIS environment setup issues across team machines | Technical | 2 | 2 | 4 | Dockerize early; single docker-compose for consistent local setup | Shirin
R-07 | API keys/credentials accidentally committed to GitHub | Security | 2 | 4 | 8 | .env + .gitignore from day 1; pre-commit secret scan | Shirin
R-08 | Dashboard usability confusing to first-time evaluator | UX | 2 | 3 | 6 | Wireframe review with guide before build; usability test (NFR-10) | Tanya
R-09 | Scope creep beyond MoSCoW "Must Have" list before MVP is stable | Project Mgmt | 3 | 3 | 9 | Strict MoSCoW gate; Should/Could features only after Must-haves pass tests | All
R-10 | Literature survey / dataset citation gaps flagged at evaluation | Academic | 2 | 3 | 6 | Maintain consolidated reference list; cross-check before each review | All
Score Legend:
Score ≥ 9 | High — mitigate immediately
Score 5-8 | Medium — monitor & plan mitigation
Score < 5 | Low — accept / monitor